## Sheet1
Stand up meeting date: 22/ 04/ 2024
Team's name | A8_OOP_Project
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Vanny Chan | Clone project | 30mn | 20mn | Work on UML class with team | 4h
| Read to understand about user story | 3h | 3h | start code on project | 4h
Makara Try | Clone project | 30mn | 30mm | Discuss UML class with team | 4h
| Read to understand about user story | 3h | 2h30mn
Hay Sav | Create repositories and create folder and file in project | 2 | 1h30mn | continue with user story and work on UML class with team | 4h
| Spending time to understand about user story | 2h30mn | 2h30mn | start code | 4h
Stand up meeting date: 24/ 04/ 2024
Team's name | A8_OOP_Project
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Vanny Chan | Worked on UML class with team | 4h | 4h | continue code on passenger file | 4h
| strat code on project with passenger | 3h | 3h
Makara Try | Worked on UML class with team | 4h | 4h | continue code on Employee | 4h
| Reasearch some syntax and start code on Employee | 3h | 3h
Hay Sav | Worked on UML class with team | 4h | 4h | continue with booking | 4h
| start code on Person and Booking | 4h | 4h